## qa_summary
Overall progress of the QA cycle(Ontime | delayed | Stopped) | On time
Total number of test cases | 45 |  |  | PASS % = (Passed test cases/Executed test cases)*100
Number of testers | 2 |  |  | (30/35)*100
Test cycle duration | 7 days |  |  | 85.71%
Status for
Number of test cases planned | 15 | The gap in the total executed and planned can be absorbed by the QA team |  | Defects density = total defects found/ test duration
Number of test cases executed | 12 |  |  | 5/3 = 1.67 defects/day
Number of test cases executed overall | 35
Number of defects encountered today | 1
Number of defect encountered so far | 5 |  |  | Critical defects % = (critical defects / total defects)*100
Number of critical defects- still open | 1 |  |  | (1/5)*100 = 20%
Overall status
Number of test cases planned | 45
Number of test cases executed | 35
Pass Percentage of the defects | 85%
Defects density | 1.2 per day
Critical defects percentage | 20%

## detailed status
Module | Scenarios | Sub Levels | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Authentication | Login | Valid credentials | Medium | Tester A | 2026-05-05 | Pass
|  | Invalid credentials | Medium | Tester A | 2026-05-05 | Pass
Authentication | Register | Add new employee | Complex | Tester B | 2026-05-05 | Pass
|  | Email already exists | Medium | Tester B | 2026-05-05 | Fail | 101: Validation error message not shown | 2- Medium | Open
Admin Dashboard | User Management | Add Trainer | Complex | Tester A | 2026-05-06 | Pass
|  | Delete Employee | Complex | Tester A | 2026-05-06 | Pass
Trainer Dashboard | Course Management | Create Training | Complex | Tester B | 2026-05-06 | Pass
|  | Edit Training | Complex | Tester B | 2026-05-06 | Fail | 102: Submit button disabled on edit | 1- High | Assigned
|  | Delete Training | Complex | Tester B | 2026-05-06 | Blocked | 102
Employee Dashboard | Enrollments | View available trainings | Medium | Tester A | 2026-05-07 | Pass
|  | Enroll in training | Complex | Tester A | 2026-05-07 | Pass
|  | My Enrollments view | Medium | Tester A | 2026-05-07 | Not executed

## Bug report
Defect ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
1 | Validation error message not shown when registering with an existing email | 1. Go to the Registration page 2. Enter an email address that is already registered in the system 3. Fill out the rest of the required fields 4. Click on the 'Register' button Expected result: A validation error message should appear stating 'Email already exists' Actual Result: No error message is shown, and the user remains on the registration page without feedback. | 2- Medium | Open | Tester B | Dev Team
2 | Submit button is disabled on Edit Training form | 1. Login as a Trainer 2. Navigate to the 'Trainer Dashboard' 3. Click on the 'Edit' button for an existing training course 4. Modify any field (e.g., Course Name or Description) 5. Attempt to save the changes Expected result: The 'Submit' button should be enabled after a change is made Actual Result: The 'Submit' button remains disabled, preventing the user from saving their updates. | 1- High | Assigned | Tester B | Frontend Developer